## Change Calendar
Change ID | Date | Service | Description | Risk | Status | Owner
CHG0090101 | 2026-09-20 | mfs-payment-gateway | Deploy payment processing v2 | Low | Closed | Raj Patel
CHG0090201 | 2026-09-22 | mfs-payment-gateway | Deploy tokenization HSM integration | Moderate | Closed | Arjun Deshmukh
CHG0090301 | 2026-09-25 | mfs-payment-gateway | Deploy idempotency key service | Low | Closed | Alex Kim
CHG0090401 | 2026-09-27 | mfs-fraud-engine | Deploy fraud scoring model v2 | Moderate | Closed | Raj Patel
CHG0090501 | 2026-09-29 | mfs-txn-monitor | Deploy velocity monitor | Moderate | Closed | Li Wei
CHG0090601 | 2026-10-02 | mfs-aml-engine | Deploy AML rule engine v1 | High | Authorized | Raj Patel
CHG0090701 | 2026-10-05 | mfs-kyc-engine | Deploy KYC document verification | Moderate | New | Nadia Kowalski
CHG0090801 | 2026-10-07 | mfs-case-engine | Deploy case management routing | Low | Assess | David Okoye